ENC 2 Ivy Medical Group – Patient Participation Group: ACTION LOG Updated 30 October 2023

| MEETING DATE | ACTION | OWNER | BY WHEN | PROGRESS | NEW COMPLETION DATE | FOLLOW-UP ACTION |
| --- | --- | --- | --- | --- | --- | --- |
| 29-06-23 | - Include action log on website and signpost on social media | Tracy Madge | 31-03-23 |  | 30-11-23 | Awaiting new website training |
|  | - U18 survey to be progressed | Steve Scott | 31-03-23 |  | 30-10-23 |  |
|  | - Letter from IMG to U18 leads once U18 survey completed | Dr Panesar | 30-10-23 |  |  |  |
|  | - IMG to discuss with system one to address updating the named pharmacy options for EPS | Melanie Maddock | 30-09-23 |  |  |  |
|  | - James Hastings from NHS Digital to support patients with NHS App in receptions by 10 July 2023 | Bob Barrett | 10-07-23 | Complete |  |  |
|  | - IMG to keep PPG updated on the Patient Triage service. Case Study update at November AGM. | Dr Panesar and Melanie Maddock | 06-11-23 |  |  |  |
|  | - PPG to facilitate two workshops to support use of Patient Triage. | Bob Barret, Tracy Madge and Liz Breeze | 31-08-23 |  |  |  |
|  | - Upload the premises presentation on IMG website and social media | Tracy Madge and Melanie Maddock | 02-07-23 |  |  | Awaiting new website training |
|  | - Arrange patient/public drop in sessions for premises updates | Tracy Madge and Steve Scott | 02-07-23 |  |  |  |
|  | - IM to meet with Parish Council and Assura to discuss premises within practice geography | Tracy Madge and Steve Scott | 12-07-23 |  |  |  |
|  | - IMG to meet with Parish Council to improve communications | Dr Panesar and Tracy Madge | 18-07-23 |  |  |  |
|  | - IMG delegated premises communication with patients and Assura to Steven Scott and Tracy Madge | Tracy Madge and Steve Scott | 29-06-23 |  |  |  |
|  | - Jeanette Johnson to feedback on using telephone access only at November AGM 2023 | Jeanette Johnson | 06-11-23 |  |  |  |
|  | - Post meeting action: PPG to reinforce that the meeting is non-political at future meetings and restate the terms of reference and code of conduct | Steve Scott | 06-11-23 |  |  |  |
|  | - PPG to make sure information is spread across the villages | Liz Breeze and Dan Howarth | 30-08-23 |  |  |  |
|  | - Send TM details of Lambley magazine by end of July 2023 | Lindsay Hall | 31-07-23 |  |  |  |
|  | - Ensure PPG access to IMG website | Melanie Maddock | 30-07-23 |  |  |  |
|  | - Post meeting action: remove Q&A from agenda and replace with questions from non-core members at the start of the meeting with responses against the relevant agenda items | Tracy Madge | 06-11-23 |  |  |  |
|  | - PPG agreed to change start of meeting to 18:15 – 19:45 | Tracy Madge | 06-11-23 |  |  |  |
|  | - Next PPG socials to be arranged by end of July 2023 | Tracy Madge | 06-11-23 |  |  |  |
|  | - Post Meeting – Jane Barber requested to be a core PPG member. To be approved at next meeting | Steve Scott | 06-11-23 |  |  |  |
| 24-11-22 | - Provide an overview of complaints and issues at every PPG | Mel Maddock | 02-03-23 |  |  |  |
|  | - Role description of team to be on Ivy website | Mel Maddock | 09-12-22 |  |  |  |
|  | - Staff photos to be on Ivy website | Mel Maddock | 09-12-22 |  |  |  |
|  | - Editor access for chair and secretary to PPG page on Ivy website to allow timely communication | Dr Panesar | 02-12-22 |  |  |  |
|  | - Terms of reference – if no comments by 09-12-22 these are approved. | Tracy Madge | 09-12-22 |  |  | To be reviewed on 6 November 2023 (AGM) |
|  | - PPG Contact list to be shared and updated as needed - publish on Ivy website | Tracy Madge | 09-12-22 |  |  | To be reviewed on 6 November 2023 (AGM) |

| Complete actions - closed |  |  |  |
| --- | --- | --- | --- |
| 02-03-23 | - EOL survey link with church, TM to supply contact details to LH | Lindsay Hall | 02-07-23 |
|  | - EOL questionnaire by end of April to PPG and IMG for approval, to issue survey in June | Lindsay Hall | 30-06-23 |
|  | - Articles for dissemination via newsletters and church outlets. to be issued on social media village pages | Bob Barrett, Liz Breeze and Tracy Madge | 31-03-23 |
|  | - BB to set up NHS App workshops by April 2023 | Bob Barrett | 30-04-23 |
|  | - TM to update on new premises developments at next PPG | Tracy Madge | 29-06-23 |
|  | - Upload Dr P update letter on the website | Melanie Maddock | 31-03-23 |
|  | - Lowdham patient survey to be issued by MM. BB to review survey w | Melanie Maddock | 31-03-23 |
|  | - LB to update PPG notice boards and provide paper copies of information for non-tech patients via an information box | Liz Breeze | 31-03-23 |
| 24-11-22 | - Listening exercise summary published on website more work required to include engagement with other age groups – U18 and over 65 | Tracy Madge | 02-03-23 |
|  | - Identify all patients who do not use technology or mobile phones for postal communication | Mel Maddock | 02-12-22 |
|  | - Core members to seek 3 new core members | Core members | 12-12-22 |
|  | - Install new doors at Lambley Lane | Mel Maddock | 01-01-23 |
|  | - Electronic Prescription Service to be launched | Mel Maddock | 01-01-23 |
|  | - Approval of vision and code of conduct. | Steve Scott | 24-11-22 |