ENC 2 Ivy Medical Group – Patient Participation Group: ACTION LOG Updated 1 July 2025

| MEETING DATE | ACTION | OWNER | BY WHEN | PROGRESS | NEW DATE | FOLLOW-UP ACTION |
| --- | --- | --- | --- | --- | --- | --- |
| 16-12-24 | - NHS app and triage targeted education to diabetes | BB/TM | 09-12-24 |  | 10-10-25 | Diabetic clinics commenced and U18 project started; agree next cohort at July meeting |
|  | - PPG support for patient use of heath check machine | TM/LB | 01-04-25 |  | 17-07-25 | Awaiting practice start date |
|  | - PPG support to premises | BB/PP |  |  | 17-07-25 | Agree next steps |
| 29-06-24 | Engagement Plan Action Log |  |  |  |  |  |
|  | - Patient Triage (PT) comms and support | PP/TM/BB | 27/5/24 |  | 31-08-24 01-04-25 | Rolling action |
|  | - Human stories on web and shared | AB | 27/5/24 |  |  | Delayed due to practice pressures. |
|  | - You said we did on notice boards and all comms sources | TM/LB | 27/5/24 |  | 01-04-25 | Ongoing |
|  | Practice Performance Action Log 25-4-24 |  |  |  |  |  |
|  | - Lowdham outreach services | PP | 27-05-24 |  | 31-08-24 01-04-25 17-07-25 | Awaiting staffing to be stable |
|  | - Repair loop induction | MM | 27/5/24 |  |  | New one on order |
|  | - Chairs update in parish mags | MM | As per publication dates |  |  | Rolling action |

|  | Complete actions - closed |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| July 2025 |  | - Feedback on meeting clashes with social prescribing sessions |  | TM | 01-04-25 |  |  |  |  |  |  |
|  |  | - BB to develop blood test flow chart – agreed to signpost to NHS App for accessing results |  | BB | 30/5/24 |  |  | 31-08-24 01-04-25 |  |  |  |
|  |  | - Provide microphone to enable PPG attendees to hear the meeting better – agreed to ask attendees and members to speak up and check regularly with attendees |  | MM | 09-12-24 |  |  |  |  |  |  |
|  |  | - Who’s who/roles inc. GP trainees – completed annually as part of annual report |  | BB | 30/7/24 |  |  | 31-08-24 01-04-25 |  |  |  |
| April 2025 |  | - Letter for non-tech users |  | TM | 16-12-24 |  |  |  |  |  |  |
|  |  | - IMG to discuss with system one to address updating the named pharmacy options for EPS. As Ivy is a dispensing practice the system does not allow this to be switched on - close action |  | PP |  |  |  |  |  |  |  |
|  |  | - Staff photos to be on Ivy website (with their permission). Agreed to not pursue photos. |  | MM |  |  |  |  |  |  |  |
|  |  | - PPG to support Ivy in implementing CQC recommendations |  | BB |  |  |  |  |  |  |  |
|  |  | - Triage patient education first cohort diabetes |  | PP |  |  |  |  |  |  |  |
|  |  | - Communicate how to change practice on website |  | MM/TM | 27/5/24 |  |  |  |  |  |  |
|  |  | - Communicate how general practice has changed at social prescribing meets and online |  | BB/TM | Bi-monthly |  |  |  |  |  |  |
|  |  | - Produce performance infographic |  | TM | 30/5/24 |  |  |  |  |  |  |
|  |  | - Inform 111 that appts are for triage only NOT consultations |  | MM | 02/05/24 |  |  |  |  |  |  |
|  |  | - Private letters comms |  | TM/LB | 27/5/24 |  |  |  |  |  |  |
|  |  | - PT training to Pharmacy to log queries |  | BB/MM | 27/5/24 |  |  |  |  |  |  |
|  |  | - Amend message regarding Rx as not all ready immediately |  | MM/PP | 02/5/24 |  |  |  |  |  |  |
|  |  | - PPG member listening session dates, all to offer support if possible |  | Members | 30/9/24 |  |  |  |  |  |  |
|  |  | - U18 engagement new member to be at next meeting and letter to Brandon to thank him |  | CL | 30/9/24 |  |  |  |  |  |  |
|  |  | - Change PT message when at capacity to simpler language |  | MM/TM | 03/05/24 |  |  |  |  |  |  |
|  |  | - Reception training on NHS App |  | BB/Elaine (NHS officer) | 27/5/24 |  |  |  |  |  |  |
|  |  | - Social media response and policy approval to be granted if no comments received by deadline. Uplifted onto Ivy website |  | Members/MM | 30/4/24 |  |  |  |  |  |  |
| 17/07/24 |  | - Members to feedback on any changes to the plan |  | Members | 30/4/24 |  |  |  |  |  |  |
|  |  | - Develop high level quarterly performance report |  | MM | 30/7/24 |  |  |  |  |  |  |
|  |  | - Amend Terms of Reference |  | M Ma | 30/5/24 |  |  |  |  |  |  |
|  |  | - Letter from IMG to U18 leads once U18 survey completed |  | Dr Panesar (PP) and Clare Leggett | 30-10-24 |  |  | 30-05-24 |  | - Letter not requested students added to CVs |  |
| 25/4/24 |  | - Enquire whether Dan needs further assistance to attend PPG meetings |  | TM | 30/5/24 |  |  |  |  |  |  |
|  | 09-12-23 |  | - Add patient triage updates to PPG work plan | Martin Maynes (MMa/Tracy Madge (TM) |  | 30-03-24 |  |  |  |  |  |  |
|  |  |  | - Add health awareness themes to work plan for 2024 – Kidney, Under 18s, prostate, diabetes, Blood Pressure, healthy eating | Bob Barrett (BB) |  | 30-03-24 |  |  |  |  |  |  |
|  |  |  | - Adopt BMA guidelines to social media comments and signpost to complaints process | TM |  | 01-01-24 |  |  |  |  |  |  |
|  | 29-06-23 |  | - Editor access for chair and secretary to PPG page on Ivy website to allow timely communication | Dr Panesar |  | 02-12-22 |
|  |  |  | - PPG Contact list to be shared and updated as needed - publish on Ivy website | Tracy Madge |  | 09-12-22 |
|  |  |  | - Include action log on website and signpost on social media | Tracy Madge |  | 31-03-23 |
|  |  |  | - U18 survey to be progressed | Steve Scott |  | 31-03-23 |
|  |  |  | - James Hastings from NHS Digital to support patients with NHS App in receptions by 10 July 2023 | Bob Barrett |  | 10-07-23 |
|  |  |  | - IMG to keep PPG updated on the Patient Triage service. Case Study update at November AGM. | Dr Panesar and Melanie Maddock |  | 06-11-23 |
|  |  |  | - PPG to facilitate two workshops to support use of Patient Triage. | Bob Barrett, Tracy Madge and Liz Breeze |  | 31-08-23 |
|  |  |  | - Upload the premises presentation on IMG website and social media | Tracy Madge and Melanie Maddock |  | 02-07-23 |
|  |  |  | - Arrange patient/public drop in sessions for premises updates | Tracy Madge and Steve Scott |  | 02-07-23 |
|  |  |  | - IM to meet with Parish Council and Assura to discuss premises within practice geography | Tracy Madge and Steve Scott |  | 12-07-23 |
|  |  |  | - IMG to meet with Parish Council to improve communications | Dr Panesar and Tracy Madge |  | 18-07-23 |
|  |  |  | - IMG delegated premises communication with patients and Assura to Steven Scott and Tracy Madge | Tracy Madge and Steve Scott |  | 29-06-23 |
|  |  |  | - Jeanette Johnson to feedback on using telephone access only at November AGM 2023 | Jeanette Johnson |  | 06-11-23 |
|  |  |  | - Post meeting action: PPG to reinforce that the meeting is non-political at future meetings and restate the terms of reference and code of conduct | Steve Scott |  | 06-11-23 |
|  |  |  | - PPG to make sure information is spread across the villages | Liz Breeze and Dan Howarth |  | 30-08-23 |
|  |  |  | - Send TM details of Lambley magazine by end of July 2023 | Lindsay Hall |  | 31-07-23 |
|  |  |  | - Ensure PPG access to IMG website | Melanie Maddock |  | 30-07-23 |
|  |  |  | - Post meeting action: remove Q&A from agenda and replace with questions from non-core members at the start of the meeting with responses against the relevant agenda items | Tracy Madge |  | 06-11-23 |
|  |  |  | - PPG agreed to change start of meeting to 18:15 – 19:45 | Tracy Madge |  | 06-11-23 |
|  |  |  | - Next PPG socials to be arranged by end of July 2023 | Tracy Madge |  | 06-11-23 |
|  |  |  | - Post Meeting – Jane Barber requested to be a core PPG member. To be approved at next meeting | Steve Scott |  | 06-11-23 |
|  | 02-03-23 |  | - EOL survey link with church, TM to supply contact details to LH | Lindsay Hall |  | 02-07-23 |
|  |  |  | - EOL questionnaire by end of April to PPG and IMG for approval, to issue survey in June | Lindsay Hall |  | 30-06-23 |
|  |  |  | - Articles for dissemination via newsletters and church outlets. to be issued on social media village pages | Bob Barrett, Liz Breeze and Tracy Madge |  | 31-03-23 |
|  |  |  | - BB to set up NHS App workshops by April 2023 | Bob Barrett |  | 30-04-23 |
|  |  |  | - TM to update on new premises developments at next PPG | Tracy Madge |  | 29-06-23 |
|  |  |  | - Upload Dr P update letter on the website | Melanie Maddock |  | 31-03-23 |
|  |  |  | - Lowdham patient survey to be issued by MM. BB to review survey | Melanie Maddock |  | 31-03-23 |
|  |  |  | - LB to update PPG notice boards and provide paper copies of for non-tech patients | Liz Breeze |  | 31-03-23 |